## Rename-It!
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Effort estimate left | Hours worked | Reference material
Command-line execution | Highest | 7 |  |  | 10 | 20
Support wildcard in command line (*.mp3) |  | 1 | Resolved | 1 | 0 | 0
Quietly rename from cmd-line |  |  | Verified | 1 | 0 | 10
Return correct error code |  |  | Closed | 1 | 0 | 0
Create test cases to test the command-line execution |  |  | Closed | 1 | 0 | 1
Save/Load filters to XML files | Lowest | 1 | New |  | 1 | 0
Define the new format |  |  | New
Make a conversion system |  |  | New
Make and run test cases for the filters |  | 1 | Closed | 1 | 0 | 1
Provide /R support: Include recursively |  |  | Closed | 1 | 0 | 0
Provide /A support: Include all files |  |  | New |  | 0
Provide /SILENT |  |  | New |  | 0
Provide /LOG file support |  |  | New |  | 0
Provide /V support |  |  | New |  | 0
Save the "rename what" in the RIT | High |  | Closed | 1 | 0 | 1
Improve speed | High | 5 | Closed | 1 | 0 | 7
Keep a compiled and studied PCRE | Lowest |  | Closed | 1 | 0 | 1
New button style | Highest | 10 | Assigned | 1 | 20 | 0
Improved Search&Replace | High | 8 | Assigned | 2 | 5 | 14
Advanced Change Case | High | 3 | Closed | 1 | 0 | 4
Colour wildcards | Normal | 1 | Closed | 1 | 0 | 2
Colour RegExp | Low | 4 | Closed | 1 | 0 | 8
Provide link to RegEx help | Normal | 1 | Assigned | 2 | 2 | 0
Smart title case | Low | 2 | Assigned | 2 | 4 | 0
Add POSIX RegExp classes | Lowest | 1 | Assigned | 2 | 1 | 0 | http://www.journaldunet.com/developpeur/tutoriel/out/051219-posix-expressions-entre-crochets.shtml
Bugs
Filter edition cancelling doesn't work | High |  | Assigned | 2
Fix unicode support | High | 1 | New |  | 2 | 0
Memory leak when adding filters and exit application | Low | 1 | Closed | 1 | 2
Fix the wildcards | Low | 2 | Closed |  | 0 | 3
// FIXME: What if the strFilename has "*" in it. |  |  | Closed
"*** FILENAME" not correctly kept by CFileName |  |  | Closed
FIXME in CRenamer::RenameAllFiles(): "What if there is more than once successor?" |  |  | Closed
Wizards | High | 5 | Assigned | 2 | 10 | 0
Crop |  | 1 | Assigned | 2 | 2 | 0
ID3 Tag |  | 1 | Assigned | 2 | 2 | 0
Enumeration |  | 1 | Assigned | 2 | 2 | 0
Change Case |  | 1 | Assigned | 2 | 2 | 0
Make the context help work | High | 3 | Assigned | 2 | 6 | 0
Comment filter | Low | 2 | Assigned | 2 | 4 | 0
Support directory and full-path renaming | Normal | 4 | Assigned | 2 | 10 | 0
Full path in preview | Normal | 2 | Assigned | 2 | 4 | 0
Test full path | Normal | 1 | Assigned | 2 | 2 | 0
Warn when before changing the path when renaming only the filename or ext |  |  | New |  | 2 | 0
Add folders to the renaming list | Normal |  | New |  | 1 | 0
Detect before renaming files opened in exclusive mode | Low | 1 | New
Rename error dialog | Normal |  | New |  | 0
Implement RenameErrorDlg detail button |  |  |  |  | 0
Implement RenameErrorDlg revert function |  |  |  |  | 0
Add try{}catch{} to catch errors | Lowest | 1 | New |  | 1 | 0
External processor | Normal |  | New
External processor filter | Normal | 4 | New |  | 8 | 0
Allow forced renaming even when errors are detected | Low | 1 | New |  | 2 | 0
Ability to define the default Search&Replace settings | Normal | 4 | New |  | 8 | 0
Order by filename | Normal | 1 | New |  | 2 | 0
Make it auto for the drag&drop & shell ext |  | 1 | New |  | 1 | 0
Right click context menu |  | 1 | New |  | 1 | 0
Internal Drag&Drop support | Normal | 4 | New |  | 8 | 0
Drag&Drop to order the filters | Normal | 1 | New |  | 2 | 0
Drag&Drop to order the files/folders | Normal | 1 | New |  | 2 | 0
Drag&Drop to add a filter | Normal | 2 | New |  | 4 | 0
Display progress | Normal |  | Verified | 1
Display verification progress |  | 2 | Verified | 1 | 0 | 1
Display renaming preparation progress |  | 2 | Verified | 1 | 0 | 1
Display a progress bar while renaming |  | 1 | Verified | 1 | 0 | 2
Don't display it for very short operations | Low | 1 | Verified | 1 | 1 | 0
Allow cancelling | Low | 1 | New |  | 2 | 0
Duplicate Filter function | Normal | 1 | New |  | 2
Load appends the filters | Low | 1 | New |  | 2
Copy/Paste filter(s) | Low | 2 | New |  | 4
Filters backward compatibility | Low | 1 | New |  | 2
Replace invalid characters | Lowest | 1 | New |  | 2
Add files improved | Lowest | 2 | New |  | 4
After uninstall, show the survey page | Low | 1 | New |  | 2
Make a bench test with 1000 files | Low |  | Closed | 1 | 0 | 0
Total |  |  |  | 2 | 154 | 76 | 1
| Priorities |  | States | Cur. Iter.
| Urgent |  | Unconfirmed | 2
| Highest |  | New
| High |  | Assigned
| Normal |  | Resolved
| Low |  | Verified
| Lowest |  | Closed
Reopen
Note on A2: Can be executed from the command-line using pre-defined filters. To just load files and/or filters: RENAMEIT [/F filter_file] [path [/R] [/A] [...]] To do the renaming from the command line (possibly without any windows): RENAMEIT /X /F filter_file path [/R] [/A] [path [/R] [/A] [...]] [/SILENT] [/LOG log_file [/V]] /X Execute the renaming. /R Preceeds the filter file. path: Path to a file or folder with possibly wildcards. /R Recursively add file/folders of the previous file_or_folder /A Including all files including system files. /LOG Log the ouput and errors in a file instead of displaying them on the screen. /V Also include files correctly renamed in the log file.
Note on A4: Don't display any messages after renaming from the command-line and exit
Note on A7: Because XML works in Unicode and ANSI for all languages.
Note on A13: support to rename without displaying any blocking message ever, nor showing the main window
Note on A15: Be more verbose (include correctly renamed files)
Note on A17: Renaming many files with the current version is very slow. Pbm: CListCtrl::InsertItem Solutions: - Virtual list control Possible Pbm: Selecting items then sorting changes the selection - Owner draw - In another thread - SetItemCount - Don't use CExplorerListCtrl Possible Pbm: Long calculation of the display path Possible Solutions: Lazy calculation of those only when required to draw the elements. further the calculated elements could be saved. Even further they could be calculated in another low level thread.
Note on A19: Look like those of PS
Note on A21: Change case can change the case of the replaced part only.
Note on A23: Wernight: Lex, Yacc? Existing lib? Buy from PowerGrep?
Note on A25: Wernight: ex: 013. - The Reurn of Jesus and, or of, it...
Note on A26: POSIX: [[:alpha:]] [[:alnum:]] [[:digit:]] [[:space:]] [[:word:]] [[:^word:]] not a word char Non-greedy: *? Match 0 or more times +? Match 1 or more times ?? Match 0 or 1 time {n}? Match exactly n times {n,}? Match at least n times {n,m}? Match at least n but not more than m times
Note on A31: We can use RegExp after escaping the string and replacing * and ? By RegExp counter-parts. But RegExp is not exactly unicode (?).
Note on A46: When adding the folder XXX: Add the following to the list: XXX\ <-- folder XXX\FILE <-- file XXX\FILE2 <-- file XXX\SUBFOLD1\ <-- folder (if recursive is checked) XXX\SUBFOLD1\FILE1 <-- file (if recursive is checked) Note: Removing a folder is not equivalent to removing a all the files of the folder. Problem: Should we rename - XXX\ - XXX\SUBFOLD1\ or only - XXX\SUBFOLD1\ ? Intuitively what does the user expect?
Note on A53: Possibilité d'utiliser un programme externe pour modifier le nom du fichier d'un façon quelconque. Par exemple ce qui est sorti dans le stdout. Pbm: Comment mixer le nom du fichier avec le stdout? Si y'a des info manquantes. Ex: Le stdout continue le nom du changeur d'un fichier audio fourni. Comment rajouter ce titre? Solution: [x] Replace filname by: "$(FullPath) $(StdOut)"
Note on A54: Wernight: The previewed new filename may be different from the real new filename used when renaming; thus, it should be possible to force the renaming.
Note on A55: Alt.: The default settings are defined depending on the usually used settings. Fusion: Once a user used to always change some settings, ask him if he wants to use those by default every time he starts the application.
Note on A62: Like layers in PhotoShop
Note on A70: Wernight: Quand on charge des filtres demander si on veut effacer les filtres actuels (sinon il ne fait qu'ajouter aux filtres actuels et ne change pas la partie à renommer.
Note on A72: Old users should be able to use their old saved filters in this new version.
Note on A73: Wernight: Proposer de remplacer les caractères invalides \ / : * ? " < > ¦ par - - - _ _ '' ( ) -. Utile surtout pour les ID3. Ceci peut être fait par un wizard. Si il y a des caractères invalides au moment où l'utilisateur clique sur Renommer, proposer d'ajouter un tel filtre automatiquement.
Note on A74: Wernight: Bouton "Add files/folders" qui affiche une boîte de dialogue avec des cases à cocher pour les dossier et la possibilité de cocher un ou tous les sous-dossiers. Se rappel d'où il était au départ de la dernière fois qu'on a validé. Un peu comme PowerGREP
Note on A76: Wernight: Before: 1, 2, 3, 4… 999, 1000 After: 2, 3, 4, 5… 999, 1

## Template
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assig-ned To | Effort estimate left (hours) | Hours worked | Reference material
<<Columns in light blue color (E-H) are typically used when a Work Item is assigned to an iteration.
The other columns are typically used regardless of whether the work item is assigned to an iteration or not.>>

## Sample
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assig-ned To | Effort estimate left (hours) | Hours worked | Reference material
Produce draft vision | 1 | 2 | Closed | 1 |  | 0 | 18
Support basic order entry process | 1 | 8 | Closed | 1 | Lisa | 0 | 56 | <UC:Inventory Control>
Prototype UI |  |  | Closed | 1 | Ann | 0 | 5 | <User Interface Guidelines.pdf>
Do the design |  |  | Closed | 1 | Lisa, Ann, Johan | 0 | 8
Implement and test server portion |  |  | Closed | 1 | Ann | 0 | 23
Implement and test client portion |  |  | Closed | 1 | Johan | 0 | 14
Update end user documentation |  |  | Closed | 1 | Lisa | 0 | 6
Finalize the Vision | 1 | 1 | Resolved | 2 | Peter | 2 | 12 | <Vision.doc>
Complete the order entry process | 2 | 8 | Verified | 2 | Johan | 2 | 66 | <UC: Order Entry>
Confirmation page displays incorrect date | 2 |  | Closed | 2 | Johan | 0 | 23
Sort orders by name | 2 |  | Closed | 2 | Ann | 0 | 18
Sort orders by order number | 3 |  | Verified | 2 | Johan | 2 | 25
Play happy sound when order is complete | 5 |  | Closed (out of scope)
Support simple inventory control | 2 | 8 | Assigned | 3 | Lisa | 70 | 0 | <UC:Inventory Control>
Prototype UI |  |  | Resolved | 2 | Ann | 10 | 0 | <User Interface Guidelines.pdf>
Do the design |  |  | Assigned | 3 | Lisa, Ann, Johan | 12 | 0
Implement and test server portion |  |  | Assigned | 3 | Ann | 14 | 0
Implement and test client portion |  |  | Assigned | 3 | Johan | 28 | 0
Update end user documentation |  |  | New | 3 | Lisa | 6 | 0
Allow disconnected use | 5 | 100 | New |  |  |  |  | <Long term vision.doc>
Produce demo for Supply Chain 2007 Conference | 3 | 5 | Assigned | 3 | Ann | 18 | 2
Edit end user documentation | 2 | 5 | Assigned | 3 | Lisa | 65 | 11
Edit install manual | 2 | 1 | Assigned | 3 | Lisa | 5 | 4
Edit release notes | 2 | 1 | Assigned | 3 | Johan | 4 | 4
Edit online help | 3 | 2 | Assigned | 3 | Ann | 22 | 3
Edit training course | 4 | 3 | Assigned | 4 |  | 34 | 0 | <Supply Chain 101.ppt>
Note on A1: Example introduction: A red triangle in upper right corner of cell means that you can right click and view comment, which provides explanatory text. This example shows a small Work Items List for a team that just finished iteration 2, has planned iteration 3, and have done a few hours of work on iteration 3. A real Work Items List would have many more entries. Columns in light blue color (E-H) are typically used when a Work Item is assigned to an iteration. The other columns are typically used regardless of whether the work item is assigned to an iteration or not.
Note on D3: The states used in this example are the same as recommended by Eclipse for their bugs; New, Assigned, Resolved, Verified, and Closed. You may need to define your own states.
Note on A4: You often divide a scenario into smaller functional tasks that enables you to more easily track progress.
Note on B4: Since you want to make sure that you deliver something of value, you need to do all of the child tasks for this work item. If that would not fit within an iteration, you should narrow the scope to include less functionality in this iteration (and moving the rest of the work to future iterations). You will still do design, implementation and testing of a complete set of functionality.
Note on C5: Typically, you do not do size estimates for child work items that are not meaningful deliverables by themselves. You break down to these small work items to enable effective planning and tracking, but they are typically not prioritized and size estimated independently.
Note on D10: This is an example of a work item where all work was not completed within an iteration as planned. A couple of hours is left to be completed in iteration 3.
Note on A11: When you have more complete use cases, versus incmplete scenarios, you can more easily divide the remainder of the use case into additional capabilities, each providing end user value, instead of doing a functional decomposition into subtasks, where the subtasks do not add value by themselves.
Note on D14: This is an example of a work item where all work was not completed within an iteration as planned. A couple of hours is left to be completed in iteration 3. This also prevents the parent work item to reach state Closed.
Note on D15: This work item is out of scope for the project. Some teams have an iteration "100" that is used to denote that it is for a fictive future iteration.
Note on C22: Since the Work Item is huge, the team put down 100 as estimate. It does not matter if the correct number is 70 or 150, since it is still a low priority. In the future, as the priority is higher, the team needs to improve their estimate, and break it down into more manageable child-work items that can be prioritized independently.
Note on F28: Since planning for iteration 4 has not yet started, nobody is assigned to this task yet.